AWARD DECISION COPY | FY27

PROPOSED SABER TASK ORDER AWARD SUMMARY

Runway 10/28 approach-light restoration

| Requirement | AF-27-014 ¦ Runway 10/28 approach-light restoration |
| --- | --- |
| Proposed order | SM-SABER-01 ¦ Task Order 27-052 ¦ Firm-fixed-price |
| Prime / disclosed sub | Outer Heaven Builders, LLC / Northern Beacon Electric, LLC |
| Value / funds | $7,350,000 ¦ FY24 Military Construction, Air Force (3300) |
| Performance | Interim operating configuration: NTP + 10 days ¦ Complete: NTP + 20 days |
| Liquidated damages | $8,500 per calendar day under RFO FAR 52.211-12 |

# Requirement and proposed award

A series of irregular hailstorms during 2026 broke nearly all approach lights serving Runway 10/28. Airfield Operations (713 AOS) requires urgent restoration before the next severe-weather season. Work includes light assemblies, foundations, cabling, transformers, control interfaces, testing, and an interim operating configuration. Access to base does not necessarily constitute access onto the flightline. Because timely performance is exceptionally important and the probable operational harm from delay is difficult to quantify precisely, the proposed order includes the RFO FAR 52.211-12 rate shown above. The construction limits are inside the controlled flightline. No award or notice to proceed has been issued.

# Award-package inventory

| Award-package element | File status |
| --- | --- |
| Scope, phased restoration plan, and 30% design remaining | Included / technically approved |
| Certified funding request and project-authority review | Included / complete |
| Government estimate, SABER coefficients, and price analysis | Included / complete |
| Wage determination, clauses, bonding, and insurance requirements | Included / complete |
| Safety, environmental, and operational phasing coordination | Included / complete |
| Prime/subcontractor roster and installation-entry sponsorship | Approved - base access |
| Proposed task order and award memorandum | Prepared for CO decision |

ACCESS RECORD IN THIS PACKAGE. Security Forces (713 SFS) approved the named personnel for installation entry and all nonrestricted base locations through 30 September 2027. The work site lies beyond the controlled flightline gate. Airfield Operations (713 AOS), with Security Forces, administers the separate work-area authorization, restricted-area endorsement, and vehicle or pedestrian permissions used inside that boundary.

REVIEW STATUS: The proposed order is otherwise prepared for the Contracting Officer's award decision.

Prepared by: Amelie Emmerich, Contract Specialist, 713 CONS