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MEMORANDUM FOR RECORD
Expanded Campbell Hall asbestos abatement | Task Order FA-27-005
FROM: Maj Emma Emmerich, Contracting Officer, 713th Contracting Squadron
DATE: 20 July 2027
SUBJECT: Scope determination - expanded concealed-asbestos abatement at Campbell Hall
	Contract / order
	SM-MACC-01 / FA-27-005 | Campbell Hall Phased Headquarters Renovation

	Value
	$26.40 million current order | $2.20-$3.00 million preliminary adjustment range

	Question
	Whether expanded abatement and directly related restoration inside Campbell Hall remain within the awarded task-order scope


Determination
Expanded asbestos containment, removal, disposal, monitoring, and directly attributable restoration at Campbell Hall are within the general scope of Task Order FA-27-005. This determination is limited to that response and does not address the contractor's separate building-substitution proposal.
RFO FAR 16.506(a) order-scope analysis
1. Type and place of work. The whole-building Campbell Hall order already includes selective demolition, hazardous-material controls, identified asbestos abatement, restoration, and affected systems rework. The change increases the quantity and distribution of that work inside the same facility; it does not change the end item or fundamental construction character.
2. Performance period and cost. The planning record anticipates about a four-week controlled interruption and a $2.60 million working adjustment, roughly ten percent of the current order value. Those effects require supported price and schedule analysis but do not transform the renovation into a different project.
3. Solicitation and competition. The solicitation disclosed Campbell Hall asbestos, required abatement and restoration, furnished a quantity basis, and incorporated RFO FAR 52.236-2. The increased concealed-material quantity calls for the same capabilities at the same site and would not reasonably have changed the competitive field for this order.
	ADMINISTRATIVE BOUNDARY. This determination does not decide entitlement, final price, time, funds, project authority, or certification. No additional work may proceed without a funded written modification, and no scope conclusion is made for replacing Campbell Hall work with Community Support Center work.


/s/ EMMA EMMERICH
Major, USAF | Contracting Officer, 713 CONS
20 July 2027
Legal concurrence
I concur that the narrowly described Campbell Hall asbestos work remains within the scope of SM-MACC-01 and Task Order FA-27-005 under RFO FAR 16.506(a), with entitlement governed separately by RFO FAR 52.236-2. The type and place of work, performance-period and cost effects, and impact on the original solicitation and competition support that conclusion. This concurrence does not extend to substituting the Community Support Center, which requires separate scope and competition analysis.
/s/ NAOMI HUNTER
Major, USAF | Deputy Staff Judge Advocate, 713 ABW/JA
20 July 2027
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