EXERCISE USE ONLY
PEACE WALKER INFRASTRUCTURE PARTNERS LLC
PEACE WALKER EXTRA WORK INVOICE
Task Order FA-27-005 | Amount due $32,000
	Invoice number
	PW-FA27-005-EXW-001

	Invoice date
	17 August 2027

	Bill to
	713th Contracting Squadron

	Project
	Campbell Hall phased headquarters renovation

	Payment terms
	Upon lawful Government disposition


Extra work billed
	ITEM
	DESCRIPTION
	BASIS
	AMOUNT

	Equipment
	Cold-climate ductless mini-split and manufacturer accessories
	1 lot
	$13,680

	Electrical
	Dedicated circuit, disconnect, conductors, raceway, and terminations
	1 lot
	$5,420

	Mechanical
	Line set, insulation, condensate, penetration, and weather seals
	1 lot
	$3,260

	Field labor
	Layout, installation, connections, and finish repair
	76 hr at $110
	$8,360

	Closeout
	Startup, functional test, cleanup, and turnover record
	1 lot
	$1,280

	TOTAL
	
	
	$32,000


Contractor statement of basis
Peace Walker performed this work from 11 through 13 August 2027 after its project manager submitted a $32,000 field-work proposal and the designated Government COR, 1st Lt Jack 'Raiden,' signed IB-02 with the direction to proceed before wall closeout. Peace Walker understood the signed COR authorization as Government approval and relied on it in good faith.
The dedicated unit was not included in the awarded drawings, specifications, or priced task-order work. Supporting purchase records, timecards, daily reports, startup results, and field photographs are available. This invoice states the contractor's position and is not a Contracting Officer authorization, price determination, or ratification.
/s/ HOT COLDMAN
Hot Coldman
President, Peace Walker Infrastructure Partners, LLC
17 August 2027
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