EXERCISE USE ONLY
FIELD WORK AUTHORIZATION
Peace Walker field request PW-FWR-214
	Prepared
	11 August 2027 at 0835 by Peace Walker project manager Hot Coldman

	Project
	Campbell Hall renovation | Task Order FA-27-005

	Location
	Level 2 Office 214

	Requested decision
	Proceed before wall closeout scheduled for 14 August

	Firm-fixed price
	$32,000


Proposed added work
Provide one cold-climate ductless heat-pump mini-split dedicated to Office 214. Work includes the indoor and outdoor equipment, dedicated electrical circuit and disconnect, refrigerant and condensate routing, wall penetration and seals, controls, startup, functional testing, finish repair, cleanup, and turnover records.
	PRICE
	PERFORMANCE
	TASK ORDER EFFECT

	$32,000 firm fixed price
	Install 11 through 13 August 2027
	Added equipment and work not shown in the awarded design


Government direction
Approved. Proceed with the $32,000 Office 214 mini-split now and submit the amount on an extra-work invoice. Do not delay wall closeout while waiting for separate paperwork.
/s/ JACK RAIDEN
Jack Raiden
First Lieutenant, USAF | COR, Task Order FA-27-005
11 August 2027 at 0935
Contractor acceptance
Peace Walker accepts the direction and will perform the described work for $32,000. The signed form was returned to the contractor at 0941 on 11 August 2027.
/s/ HOT COLDMAN
Hot Coldman
Project Manager, Peace Walker Infrastructure Partners, LLC
11 August 2027 at 0941
Contracting Officer block No Contracting Officer signature or written contract modification appears on this form or elsewhere in the pre-performance file.
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