EXERCISE USE ONLY
DEPARTMENT OF THE AIR FORCE
SHADOW MOSES AIR FIELD, ALASKA
BENEFIT ACCEPTANCE PRICE AND FUNDS RECORD
Campbell Hall Office 214
	System
	One cold-climate ductless heat-pump mini-split serving Office 214

	Invoice
	IB-01 | PW-FA27-005-EXW-001 | $32,000

	Inspected
	18 August 2027 by 713 CES Mechanical Systems

	Condition
	Installed, tested, operational, and retained in Government use


Technical inspection and benefit
	CHECK
	RESULT
	EVIDENCE

	Equipment and capacity
	Acceptable
	Cold-climate rating, design load, and equipment data verified

	Electrical installation
	Acceptable
	Circuit, disconnect, labeling, grounding, and testing complete

	Mechanical installation
	Acceptable
	Line set, insulation, condensate, penetration, and seals complete

	Startup and controls
	Acceptable
	Functional test passed; temperature and defrost controls operate

	Government use
	Confirmed
	Office 214 has used the system continuously since 16 August


RFO FAR 1.405(c)(1) finding The Government accepted and continues to use the benefit of a technically acceptable system. Benefit alone does not authorize payment or cure the authority defect.
Price analysis
	ELEMENT
	INVOICE
	GOVERNMENT BENCHMARK
	ANALYSIS

	Equipment
	$13,680
	$14,050
	Localized supplier catalog and freight

	Electrical
	$5,420
	$5,600
	Quantity takeoff and regional labor

	Mechanical
	$3,260
	$3,390
	Quantity takeoff and regional labor

	Field labor
	$8,360
	$8,588
	76 hours at $113 benchmark

	Closeout
	$1,280
	$1,300
	Startup, testing, cleanup, and turnover

	TOTAL
	$32,000
	$32,928
	Invoice is 2.8 percent below benchmark




PRICE DETERMINATION AND FUNDS RECORD
RFO FAR 1.405(c)(4) and (6)
Contracting Officer price determination
I compared the segregated invoice, supplier purchase records, timecards, regional labor and freight data, and the Government quantity takeoff. The $32,000 invoice is 2.8 percent below the $32,928 benchmark. I found no duplicate cost, unsupported contingency, or cost already paid under the task order. I determine $32,000 fair and reasonable for ratification purposes.
/s/ EMMA EMMERICH
Emma Emmerich
Major, USAF | Contracting Officer, 713 CONS
20 August 2027
Funds availability certification
	TEST
	RECORD
	RESULT

	Purpose
	FY24 Military Construction, Air Force, Project SM-24-001 Campbell Hall
	Appropriate project funds

	At commitment
	Unobligated balance on 11 August 2027 was $418,600
	$32,000 was available

	At ratification
	Unobligated balance reserved on 20 August 2027 was $386,600
	$32,000 remains available

	Amount
	Accounting classification 57 3300 24 713 3010 SM-24-001
	Full amount certified


Funds certification Appropriate funds existed when Raiden made the commitment and remain available now. No funds are obligated by this certification before ratification approval and the proper contract action.
/s/ ROSEMARY MARQUEZ
Rosemary Marquez
Captain, USAF | Certifying Official, 713 CPTS
20 August 2027
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